## Questions
48 hr Data Challenge
This role will require a strong knowledge of data modeling, Power BI, and the ability to quickly and accurately perform data transformations and insight generation. Please follow the below instructions to prepare for the interview.
Send back all applicable files and supporting documentation as needed.
Before the interview
1. Study the structure of the tables in this Excel document and develop a working PowerBI Dashboard to help Senior Executives make data-based decisions
Dashboard Requirements:
1. How would you track number of projects and budget over time?
2. Report Milestones in a visual to track project progress over time
Milestone dates should be greyed out if the milestone date is in the past, show a flag on the row when the projected date is later than the target date
3. Create a ledger showing budget at different levels of granularity -- such as Level 1 (Project) , Level 2 (Division), and Level 3 (Scope)
**Hint: Use conditional formatting to help end user identify when commitments are over Approved Budget
4. Design at least one visual that is only visible when a single project is selected (in a slicer or other visual). If multiple, or all, projects are selected, this visual should be hidden
5. How would you implement RLS for end users to only see the data for their team?
6. Create a framework to validate the data shared in this excel
6. Keep in mind that we value performant dashboards!
During the interview
*Be prepared to concisely explain your approach, data model, DAX, and visuals
*Be prepared to work with the data live. You may be asked to visualize other metrics, integrate new data, or perform data transformations

## Project
Project_Code | Project_ID | Start_Date | Initiation_Date | Project_End_Date | Project Manager | Design Manager | Team
XX21-0001 | 1 | 2021-02-21 | 2021-05-09 07:00 | 2021-09-29 07:00 | Mendy O'Lagen | Penni Gronous | X
XY20-0001 | 2 | 2021-01-15 | 2019-01-15 08:00 | 2022-06-01 | Susanna Muffitt | Stefa Yellowley | X
YY21-0008 | 3 | 2021-09-28 | 2021-08-02 07:00 |  | Ardelia Brombell | Georgia Kebell | Y
YY21-0015 | 4 | 2021-07-14 | 2021-12-15 07:00 |  | Charlot Cockrem | Sadie Strange | Y
XY21-0019 | 5 | 2021-10-20 | 2021-10-15 07:00 |  | Shelby Stebbins | Pamella McFeate | X

## Milestone
Project_ID | Milestone | Target_Date | Projected_Date | Actual_Date
1 | Start of Testing | 2021-09-30 | 2021-09-30 | 2021-10-30
1 | IFP | 2021-07-02 | 2021-09-16 | 2021-09-16
1 | Utilities Ready | 2021-07-06 | 2021-07-06 | 2021-07-06
1 | Land Tools | 2021-07-06 | 2021-07-06 | 2021-07-04
1 | EQL/Space Plan | 2021-05-21 | 2021-05-21 | 2021-06-21
1 | Test Fit | 2021-05-21 | 2021-05-21 | 2021-05-21
1 | D30 | 2021-12-09
2 | Start of Testing | 2021-09-30 | 2021-09-30 | 2021-09-30
2 | Utilities Ready | 2021-09-01 | 2021-09-01 | 2021-09-01
2 | Land Tools | 2021-08-23 | 2021-08-23 | 2021-08-23
2 | IFP | 2021-03-29 | 2021-03-29 | 2021-03-29
2 | D90 | 2021-03-11 | 2021-03-11 | 2021-03-11
2 | D60 | 2021-03-01 | 2021-03-01 | 2021-03-01
2 | Test Fit | 2021-01-31 | 2021-01-31 | 2021-01-31
2 | EQL/Space Plan | 2021-01-15 | 2021-01-15 | 2021-01-15
3 | Start of Testing | 2022-07-20 | 2022-07-20 | 2022-07-20
3 | Land Tools | 2022-05-31 | 2022-05-31 | 2022-05-31
3 | Utilities Ready | 2022-05-31 | 2022-05-31 | 2022-05-31
3 | IFP | 2022-01-05 | 2022-01-07 | 2022-01-07
3 | D90 | 2022-01-05 | 2022-01-05 | 2022-01-05
3 | Financial Approval | 2021-12-03 | 2021-12-22 | 2021-12-22
3 | D60 | 2021-12-08 | 2021-12-08 | 2021-12-10
3 | Test Fit | 2021-10-21 | 2021-11-05 | 2021-11-05
3 | EQL/Space Plan | 2021-10-21 |  | 0
4 | Start of Testing | 2023-02-03 | 2023-02-03
4 | Utilities Ready | 2022-12-23 | 2022-12-23
4 | Land Tools | 2022-08-16 | 2022-08-16
4 | D90 | 2022-08-04 | 2022-08-04
4 | IFP | 2022-08-18 | 2022-07-25 | 2022-07-25
4 | D60 | 2022-07-21 | 2022-07-21 | 2022-07-24
4 | D30 | 2022-07-07 | 2022-07-07 | 2022-07-07
4 | Financial Approval | 2022-01-28 | 2022-01-28 | 2022-01-28
4 | Test Fit | 2022-01-07 | 2022-01-07 | 2021-12-06
4 | EQL/Space Plan | 2021-11-30 | 2021-11-30 | 2021-11-30
5 | Start of Testing | 2022-08-19 | 2022-08-19
5 | D90 | 2022-04-08 | 2022-04-08 | 2022-04-09
5 | IFP | 2022-04-08 | 2022-04-08 | 2022-04-08
5 | D60 | 2022-03-04 | 2022-03-04 | 2022-03-04
5 | Financial Approval | 2022-01-24 | 2022-01-24 | 2022-01-24
5 | Test Fit | 2022-01-07 | 2022-01-10 | 2022-01-10
5 | EQL/Space Plan | 2021-12-20 | 2021-12-10 | 2021-12-10

## Project_Budget
Project_ID | Scope_ID | Discipline | Scope | Approved_Budget | Change_Date
3 | 592 | 00 - Design | Design Staff Augmentation | 197310 | 2022-01-26
3 | 598 | 01 - General Requirements | Permitting, Rentals, Inspections, Etc. | 147064 | 2022-01-28
3 | 600 | 02 - Existing Conditions | 13-100 - Lightning Protection | 86000 | 2022-01-28
3 | 600 | 02 - Existing Conditions | Overhead Conduit Runs | 86000 | 2022-01-28
3 | 603 | 03 - Concrete | Concrete - Pads, Rebar, Foundations, Saw Cut | 582356 | 2022-01-28
3 | 603 | 03 - Concrete | 10-300 - Fireplaces and Stoves | 582356 | 2022-01-28
3 | 607 | 05 - Metals | Steel Roll Up Doors/Ceiling Support | 46417 | 2022-01-28
3 | 607 | 05 - Metals | Contingency | 46417 | 2022-01-28
3 | 611 | 07 - Thermal & Moisture Protection | Water Proofing and Insulation | 34000 | 2022-01-28
3 | 614 | 08 - Doors / Windows/ Openings | Doors, Glazing, Roll Up Door | 146930 | 2022-01-27
3 | 616 | 09 - Finishes | Tiles, Framing, Drywall, Paint | 222809 | 2022-01-28
3 | 616 | 09 - Finishes | Civil | 222809 | 2022-01-28
3 | 625 | 22 - Plumbing | Self Perform - Condensante Drainage & Floor Drain | 123561 | 2022-01-28
3 | 625 | 22 - Plumbing | Multiple projects | 123561 | 2022-01-28
3 | 626 | 23 - HVAC | Exhaust, CDA, Chilled Water, etc. | 512257 | 2022-01-28
3 | 626 | 23 - HVAC | Walls | 512257 | 2022-01-28
3 | 631 | 23 - HVAC | Self Perform - Provide Heat & Cooling HVAC System with Ductwork Distribution | 345801 | 2022-01-28
3 | 632 | 25 - Integrated Automation | Controls | 12480 | 2022-01-28
3 | 636 | 26 - Electrical | Self Perform - Electrical Scope | 424986 | 2022-01-28
3 | 636 | 26 - Electrical | 10-300 - Fireplaces and Stoves | 424986 | 2022-01-28
3 | 641 | 26 - Electrical | Electrical Scope | 586430 | 2022-01-28
3 | 643 | 27 - Communications | Telecomm Drops | 9900 | 2022-01-28
3 | 644 | XX - Contingency | Contingency/OT Allowance | 169672 | 2022-01-28
3 | 901 | 03 - Concrete | Construction Permits | 26219 | 2022-02-17
5 | 903 | 28 - Electronic Safety & Security | Fire Alarm Install | 62117 | 2022-02-17
5 | 903 | 28 - Electronic Safety & Security | Fire Alarm Install | 62117 | 2022-02-17
3 | 909 | 03 - Concrete | 1-540 - Construction Aids | 83110 | 2022-02-17
5 | 1028 | 28 - Electronic Safety & Security | Horn StrobesDuct detectorsExit Signs | 20480 | 2022-02-18
5 | 1028 | 28 - Electronic Safety & Security | Horn StrobesDuct detectorsExit Signs | 20480 | 2022-02-18
5 | 1029 | 08 - Doors / Windows/ Openings | (1) Fire Rated 3070 HM Frame w/ Door & HardwareRoll Up Door - Exterior Metal Roll Up Door - 20' x 16' | 126882.75 | 2022-02-18
5 | 1031 | 06 - Wood & Plastic | Walls - Unistructs and glass - 4' High | 109490 | 2022-02-18
5 | 1032 | 05 - Metals | Structutal Steel for the Roll Up Door - HSS 6 X 6 X 1/2"" | 45304 | 2022-02-18
5 | 1032 | 05 - Metals | Structutal Steel for the Roll Up Door - HSS 6 X 6 X 1/2"" | 45304 | 2022-02-18
5 | 1035 | 21 - Fire Suppression | Rerouting of the existing Sprinkler Heads - Full Height Walls buildout - Allowance | 80450 | 2022-02-18
5 | 1037 | 23 - HVAC | Remove existing VAV Boxes - AllowanceInstall new (Rerouting of existing) Chilled Water Supply and Retrun Piping w/ Hot TapsInstall new (Rerouting of existing) Heating Hot Water Supply and Retrun Piping w/ Hot TapsRemoving of the existing Chilled Wate | 860616 | 2022-02-18
5 | 1037 | 23 - HVAC | Remove existing VAV Boxes - AllowanceInstall new (Rerouting of existing) Chilled Water Supply and Retrun Piping w/ Hot TapsInstall new (Rerouting of existing) Heating Hot Water Supply and Retrun Piping w/ Hot TapsRemoving of the existing Chilled Wate | 860616 | 2022-02-18
5 | 1038 | 27 - Communications | Controls Tie into existing BMS | 7038 | 2022-02-18
5 | 1038 | 27 - Communications | Controls Tie into existing BMS | 7038 | 2022-02-18
5 | 1040 | 01 - General Requirements | general requirements | 412545 | 2022-02-18
5 | 1042 | 00 - Design | Design Costs | 34197 | 2022-02-18
5 | 1043 | XX - Contingency | Contingency | 319804 | 2022-02-18
5 | 1086 | 00 - Design | Design Costs EVAL INFRA | 27176 | 2022-02-25
5 | 1087 | 00 - Design | Design Costs SEMI | 62384 | 2022-02-24
5 | 1087 | 00 - Design | Design Costs SEMI | 62384 | 2022-02-24
5 | 1088 | 00 - Design | Design Costs VSST | 29840 | 2022-02-24
5 | 1089 | 00 - Design | Design Costs FSVL | 60942 | 2022-02-24
5 | 1090 | 00 - Design | Design costs VDIN | 19815 | 2022-02-24
5 | 1091 | 00 - Design | Design Costs ROBO | 137967 | 2022-02-24
5 | 1092 | 00 - Design | Design Costs HVLV | 40650 | 2022-02-24
5 | 1092 | 00 - Design | Design Costs HVLV | 40650 | 2022-02-24
5 | 1093 | 00 - Design | Design Costs CAMR | 40690 | 2022-02-24
5 | 1094 | 00 - Design | Design Costs DSPV | 57992 | 2022-02-24
5 | 1094 | 00 - Design | Design Costs DSPV | 57992 | 2022-02-24
3 | 1104 | 06 - Wood & Plastic | Solid Surface countertops | 18400 | 2021-12-21
3 | 1104 | 06 - Wood & Plastic | Solid Surface countertops | 18400 | 2021-12-21
3 | 1131 | 10 - Specialties | Bathroom Accessories & Partitions | 64823 | 2021-12-22
3 | 1133 | 21 - Fire Suppression | Sprinklers | 74550 | 2021-12-21
3 | 1233 | 28 - Electronic Safety & Security | 1-540 - Construction Aids | 60983 | 2021-12-22
2 | 1267 | 00 - Design | Design Services | 132441 | 2022-03-11
2 | 1268 | 01 - General Requirements | Rental/Safety Equipments | 33702 | 2022-03-11
2 | 1271 | 01 - General Requirements | Concrete scanning, Drawings, Paint, Bollards | 128431 | 2022-03-11
2 | 1276 | 26 - Electrical | Materials - SP | 1123486 | 2022-03-11
2 | 1281 | 03 - Concrete | Exterior Civil Work | 276145 | 2022-03-11
2 | 1282 | 28 - Electronic Safety & Security | Fire Alarms | 25992 | 2022-03-11
2 | 1283 | 23 - HVAC | Mechanical Scope - SP | 1541693.99 | 2022-03-11
2 | 1284 | 01 - General Requirements | Other Misc. Scopes | 259125 | 2022-03-11
2 | 1285 | 22 - Plumbing | Pipe Supports | 691643.7 | 2022-03-11
3 | 1319 | 07 - Thermal & Moisture Protection | Insulation for Roof in shop | 138502 | 2022-03-13
4 | 1561 | 26 - Electrical | Electrical | 3931338.87 | 2022-03-25
4 | 1562 | 23 - HVAC | Mechanical Piping + Sheet metal Ductwork + Instrumentation and Controls | 2538428 | 2022-03-25
4 | 1563 | 23 - HVAC | Plumbing + Process Piping | 304282 | 2022-03-25
4 | 1564 | 12 - Furnishings | Tool Anchorage | 243430 | 2022-03-25
4 | 1565 | 06 - Wood & Plastic | Walls | 1058869 | 2022-03-25
4 | 1566 | 28 - Electronic Safety & Security | Fire Alarm | 327657 | 2022-03-25
4 | 1567 | 21 - Fire Suppression | Fire Sprinklers | 496100 | 2022-03-25
4 | 1568 | 02 - Existing Conditions | Demo | 43893 | 2022-02-25
4 | 1569 | 03 - Concrete | Civil | 81532 | 2022-03-25
4 | 1570 | 00 - Design | Design | 918821.97 | 2022-03-25
4 | 1571 | 01 - General Requirements | Construction Permits | 208879 | 2022-03-25
4 | 1572 | 01 - General Requirements | General Requirements - Other Project Costs (rental equipment) | 501310 | 2022-03-25
4 | 1573 | 10 - Specialties | Overhead Conduit Runs | 1923628 | 2022-03-25
5 | 1671 | 27 - Communications | Controls & Commissioning - costs removed from ROBO Lab | 16806 | 2022-04-08
5 | 1673 | 23 - HVAC | Mechanical Sheetmetal (new scope) - costs removed from Camera Lab | 14875.6 | 2022-04-08
5 | 1676 | 27 - Communications | Controls & Commissioning - costs removed from Camera Lab | 6057 | 2022-04-08
5 | 1677 | 23 - HVAC | Mechanical Sheetmetal (new) - costs removed from DSP & Audio Lab | 69705.1 | 2022-04-08
5 | 1680 | 27 - Communications | Controls & Commissioning - costs removed from DSP & Audio Lab | 12114 | 2022-04-08
5 | 1683 | 27 - Communications | Controls & Commissioning - costs removed from Eval Infra Lab | 5784 | 2022-04-08
5 | 1692 | 27 - Communications | Controls & Commissioning - costs removed from FSVL Lab | 12114 | 2022-04-08
5 | 1696 | 27 - Communications | Controls & Commissioning - cost removed from SEMI Lab | 5784 | 2022-04-08
5 | 1700 | 27 - Communications | Controls & Commissioning - costs removed from VDIN Lab | 3438 | 2022-04-08
5 | 1704 | 27 - Communications | Controls & Commissioning - costs removed from VSST Lab | 5784 | 2022-04-08
5 | 1763 | 28 - Electronic Safety & Security | Fire Alarm | 94232 | 2022-04-19
5 | 1773 | 23 - HVAC | Mechanical - Sheetmetal (new) - HVLV cost removed from labs | 25866.33 | 2022-04-20
5 | 1774 | 23 - HVAC | Mechanical - Piping (new scope) - HVLV cost removed from lab | 4218 | 2022-04-20
3 | 1813 | 07 - Thermal & Moisture Protection | Roof Infill | 194159 | 2022-04-26
3 | 1843 | 22 - Plumbing | Design | 2368.2 | 2022-05-05
5 | 1867 | 03 - Concrete | Concrete Pads - required for the audio chamber | 23200 | 2022-05-04
5 | 1868 | 23 - HVAC | VAV Funding - general air for space | 232600 | 2022-05-04
5 | 1869 | 27 - Communications | BMS Controls - controls each VAV to properly distribute the air | 118000 | 2022-05-04
5 | 1870 | 00 - Design | Design | 40900 | 2022-05-04
5 | 1871 | 05 - Metals | Roll Up Door | 23100 | 2022-05-04
5 | 1872 | 22 - Plumbing | CDA System | 120300 | 2022-05-04
5 | 1873 | 22 - Plumbing | CDA Syatem Drainage | 51200 | 2022-05-04
3 | 1879 | 03 - Concrete | 13-020 - Building Modules | 56540 | 2022-05-13
3 | 1880 | 03 - Concrete | 13-900 - Fire Suppression | 14500 | 2022-05-13
3 | 1881 | 03 - Concrete | Plumbing + Process Piping | 10010 | 2022-05-13
3 | 1900 | 22 - Plumbing | Plumbing - Relocating Piping/Plumbing around Restroom | 7051.9 | 2022-05-05
3 | 1913 | 02 - Existing Conditions | SP - CSA Team - Demo | 18572 | 2022-05-23
3 | 1915 | 09 - Finishes | Self perform - Finishes/Paint Scope | 222809 | 2022-05-25
3 | 1919 | 08 - Doors / Windows/ Openings | 2-500 - Utility Services | 60000 | 2022-05-25
3 | 1922 | 08 - Doors / Windows/ Openings | 10-150 - Compartments and Cubicles | 73616 | 2022-05-25
3 | 1925 | 05 - Metals | 16-200 - Electrical Power | 6053 | 2022-05-25
3 | 1926 | 22 - Plumbing | 2-315 - Excavation | 382891 | 2022-05-25
5 | 1930 | 26 - Electrical | Base Scope of work. Primary install, Feeders & Distribution - Self Perform | 1121174 | 2022-05-25
5 | 1932 | 26 - Electrical | MCOOL Panel Install - Self Perform | 87371.95 | 2022-05-25
3 | 2250 | 07 - Thermal & Moisture Protection | 10-300 - Fireplaces and Stoves | 30000 | 2022-06-13
5 | 2261 | 12 - Furnishings | Anchorage for Tools | 247375 | 2022-06-14
5 | 2265 | 13 - Special Construction | Cranes | 120000 | 2022-06-16
5 | 2267 | 05 - Metals | Roll Up Door | 37800 | 2022-06-16
5 | 2268 | 03 - Concrete | Concrete Footings | 5800 | 2022-06-16
5 | 2270 | 03 - Concrete | Required for the Audio Chamber | 17100 | 2022-06-16
5 | 2275 | 08 - Doors / Windows/ Openings | 13.5' Fire Rated Wall Assembly at Electrical Room, (1) Fire Rated 3070 HM Frame w/ Door & Hardware - Electrical room | 22767.5 | 2022-06-16
5 | 2276 | 08 - Doors / Windows/ Openings | Wall Base - Vinyl, Walls - Unistructs and glass - 4' High | 29537.9 | 2022-06-16
5 | 2278 | 09 - Finishes | Architectural Initial Budget | 468227 | 2022-06-16
5 | 2290 | XX - Contingency | Walls - Unistructs and glass - 4' High | 109490 | 2022-02-18
5 | 2291 | 08 - Doors / Windows/ Openings | Addendum #2 added door | 10800 | 2022-06-17
5 | 2293 | XX - Contingency | Addendum #2 added door | 10800 | 2022-06-17
4 | 2298 | 04 - Masonry | Demo | 21952.96 | 2022-06-21
4 | 2299 | 05 - Metals | Tool Anchorage | 205029.82 | 2022-06-21
4 | 2300 | 07 - Thermal & Moisture Protection | Base Scope of work. Primary install, Feeders & Distribution - Self Perform | 9754.83 | 2022-06-21
4 | 2301 | 08 - Doors / Windows/ Openings | Doors | 407894.77 | 2022-06-21
4 | 2302 | 09 - Finishes | Multiple projects | 465552.57 | 2022-06-21
4 | 2303 | 31 - Earthwork | Soil Redemption, GeoTech | 70286 | 2022-06-21
4 | 2304 | 40 - Process Interconnections | Compressed Air Drops | 27904.69 | 2022-06-21
3 | 2309 | 03 - Concrete | Mechanical Piping + Sheet metal Ductwork + Instrumentation and Controls | 98370 | 2022-06-21
5 | 2310 | 26 - Electrical | Demo of existing(no relocations) - Self Peform | 75000 | 2022-06-22
5 | 2311 | 26 - Electrical | Exit Signs & Temp Locations - Self Peform | 40270.55 | 2022-06-22
5 | 2312 | 26 - Electrical | Optimus Power - Self Peform | 2402.8 | 2022-06-22
5 | 2313 | 26 - Electrical | Steering lab - Self Peform | 42936.95 | 2022-06-22
5 | 2314 | 26 - Electrical | Camera Lab - Self Peform | 2402.87 | 2022-06-22
5 | 2315 | 26 - Electrical | Optimus Supplemental power - Self Peform | 9987.75 | 2022-06-22
5 | 2316 | 26 - Electrical | EHS Cabinet - Self Peform | 5842 | 2022-06-22
5 | 2317 | 26 - Electrical | Change Order Rev #04 - Self Peform | 160918.27 | 2022-06-22
5 | 2318 | 26 - Electrical | Electrical Original Budget | 2608172.8 | 2022-06-22
5 | 2319 | 09 - Finishes | Base Scope - Self Pefrom | 282059 | 2022-06-22
5 | 2320 | 03 - Concrete | Add Electrical Pads (CO #1) - Self Peform | 15697 | 2022-06-22
5 | 2321 | 09 - Finishes | Add Walls (CO#01) - Self Peform | 14016 | 2022-06-22
5 | 2322 | 09 - Finishes | Add Doors (CO#01) - Self Peform | 30000 | 2022-06-22
5 | 2323 | 09 - Finishes | RFI #016 - 16-gauge framing at (1) roll up openings (Just for Camera Lab) - Viktoriia working on it - Self Peform | 5491.19 | 2022-06-22
3 | 2324 | 09 - Finishes | 1-904 - Hazardous Materials Removal and Disposal | 63089.85 | 2022-06-21
5 | 2325 | 09 - Finishes | Addendum #02 (Add Door) - Approved - Self Peform | 10800 | 2022-06-22
5 | 2326 | 09 - Finishes | Exterior Door Infill (Viktoria working on it) - Self Peform | 5536.8 | 2022-06-22
5 | 2327 | 09 - Finishes | Hallway Ceiling - Self Peform | 6075.57 | 2022-06-22
5 | 2328 | 09 - Finishes | Hallway Ceiling - Self Peform | 6075.57 | 2022-06-22
5 | 2329 | 09 - Finishes | 6B Conduit Openings - Self Peform | 1658.7 | 2022-06-22
3 | 2330 | 09 - Finishes | Painting mural on the demising wall of the 6A Vehicle Shop | 30300 | 2022-06-21
5 | 2331 | 09 - Finishes | Self Peform | 7970.19 | 2022-06-22
5 | 2332 | 22 - Plumbing | Demolition - Self Peform | 83618 | 2022-06-22
5 | 2333 | 22 - Plumbing | Chilled Water & Hot water relo (CO# 1) - Self Peform | 4810 | 2022-06-22
5 | 2334 | 22 - Plumbing | CDA Install & Equipment - Self Peform | 120330 | 2022-06-22
5 | 2335 | 22 - Plumbing | CDA Install (CO# 2) - Self Peform | 8745.6 | 2022-06-22
5 | 2336 | 22 - Plumbing | Domestic Chilled Water isntall (CO#03) - Self Peform | 6700 | 2022-06-22
3 | 2337 | 23 - HVAC | 2-781 - Asphalt Pavers | 12335.44 | 2022-06-17
5 | 2341 | XX - Contingency | Contingency | 319804 | 2022-02-18
4 | 2389 | XX - Contingency | Contingency | 835517.23 | 2022-06-25
3 | 2393 | 22 - Plumbing | 10-300 - Fireplaces and Stoves | 2172 | 2022-06-27
5 | 2448 | 26 - Electrical | Install (3) 480V 20A 3-phase w/ L-1630s, (3) 120A 1-phase duplex receptacles, and (3) data drops - self-perform | 30800 | 2022-07-05
5 | 2484 | 01 - General Requirements | Abate floor tile, leveling compound and ACM mastic in 1 electrical room approx 188SF | 7709 | 2022-07-11
5 | 2489 | XX - Contingency | Walls - Unistructs and glass - 4' High | 3128 | 2022-07-15
5 | 2490 | 06 - Wood & Plastic | Door 101 LB - Exterior Finish | 3128 | 2022-07-15
5 | 2527 | XX - Contingency | Concrete Pads - required for the audio chamber | 15697 | 2022-07-20
5 | 2528 | 08 - Doors / Windows/ Openings | Remove Electrical Room Walls- CSA | 5540 | 2022-07-20
5 | 2540 | XX - Contingency | Architectural Initial Budget | 369684 | 2022-07-20
5 | 2542 | XX - Contingency | Electrical Original Budget | 1639064 | 2022-07-20
5 | 2559 | 08 - Doors / Windows/ Openings | Exterior Roll Up Door | 37800 | 2022-07-20
5 | 2560 | 08 - Doors / Windows/ Openings | Fabric Roll Up Door Original Budget | 23100 | 2022-07-20
5 | 2561 | 13 - Special Construction | Increase $$30,000: Cranes | 30000 | 2022-07-20

## Project_Committed
Scope_ID | Committed
1281 | 310389
1268 | 54306
1276 | 1158063
1283 | 1553774.99
1282 | 11437
1285 | 663332.7
1271 | 109630
1267 | 110532
1284 | 206658
598 | 130496
592 | 166910
611 | 34000
641 | 538854
2337 | 12335.44
2250 | 25282
2324 | 60725.85
1233 | 35387
600 | 58628
1913 | 15913
1319 | 130331
614 | 122019
632 | 12480
644 | 159547
643 | 50780
631 | 379502
1131 | 97031
1133 | 116316
1104 | 53888
1915 | 270531
1900 | 36931.9
1813 | 223995
626 | 542749
625 | 154264
616 | 262771
603 | 617081
607 | 72537
636 | 467403
2330 | 38252
1919 | 91414
1925 | 32918
1880 | 24770
909 | 117103
1879 | 79586
2393 | 27355
1922 | 92994
1926 | 326370
636 | 369359
603 | 546213
2309 | 115572
626 | 542128
1843 | 53563.2
1881 | 37139
600 | 134054
616 | 227966
625 | 140837
607 | 99428
1104 | 25911
901 | 37075
2299 | 222015.82
2298 | 46016.96
2300 | 16195.83
2303 | 66724
1561 | 3882838.87
1562 | 2496128
1565 | 1030964
1570 | 896487.97
1563 | 276024
1573 | 1876345
1569 | 77328
2302 | 423817.57
2389 | 821262.23
1572 | 476872
2301 | 393197.77
1566 | 267914
1567 | 470518
2304 | 66525.69
1571 | 208879
1564 | 243430
1568 | 43893
1930 | 1121174
2268 | 5800
1932 | 87371.95
2316 | 5842
2261 | 247375
1868 | 232600
1680 | 12114
1696 | 5784
1692 | 12114
1872 | 120300
1873 | 51200
1871 | 23100
1867 | 23200
2314 | 2402.87
2317 | 160918.27
2335 | 8745.6
2327 | 6075.57
1773 | 25866.33
1774 | 4218
2333 | 4810
2326 | 5536.8
1870 | 40900
1869 | 118000
2315 | 9987.75
2291 | 10800
2325 | 10800
2323 | 5491.19
2322 | 30000
1677 | 69705.1
1028 | 20480
1038 | 7038
903 | 62117
1037 | 860616
1092 | 40650
1094 | 57992
1032 | 45304
1094 | 57992
2310 | 75000
1031 | 109490
1087 | 62384
1032 | 45304
1037 | 860616
1092 | 40650
2275 | 22767.5
2278 | 468227
2276 | 29537.9
2267 | 37800
1671 | 16806
2311 | 40270.55
2265 | 120000
1028 | 20480
1089 | 60942
1087 | 62384
1091 | 137967
2270 | 17100
903 | 62117
1038 | 7038
1763 | 94232
2332 | 83618
2334 | 120330
2484 | 7709
2331 | 7970.19
1043 | 319804
2329 | 1658.7
2336 | 6700
2561 | 30000
2540 | 369684
2490 | 3128
2559 | 37800
2528 | 5540
1035 | 80450
2328 | 6075.57
2318 | 2608172.8
2313 | 42936.95
2312 | 2402.8
2319 | 282059
2321 | 14016
2320 | 15697
1042 | 34197
1029 | 126882.75
1040 | 412545
1093 | 40690
1088 | 29840
1090 | 19815
1086 | 27176
2341 | 319804
2342 | 3252
2491 | 200400.8
2290 | 109490
1704 | 5784
1683 | 5784
2293 | 10800
2448 | 30800
2527 | 15697
1700 | 3438
2489 | 3128
2542 | 1639064
1673 | 14875.6
1676 | 6057
2560 | 23100